## Sheet1
Date | Time In | Time Out | Planned Task | Accomplished Task | Tommorow Task | Blockers
2021-10-28 | 9:59 | 23:21 | TJX - POS/GSBO Azure VM - Setup Savers - Password Complexity Task | Savers - Password Complexity Task - Done TJX - GenDTF / Download Issue with TLS - Test - Done | TJX - POS/GSBO Azure VM - Setup Savers - Password Complexity Task
2021-10-29 | 9:27 | 44498.9831 | TJX - POS/GSBO Azure VM - Setup , Savers - Password Complexity HLE | TJX - POS/GSBO Azure VM - Setup , Savers - Password Complexity HLE | Waiting for new task
2021-11-02 | 44502.3991 | 19:00 | Waiting for new task | Savers - Country Support SCO - Investigation | Savers - Country Support SCO - Investigation
2021-11-03 |  | 44504.0014 | Savers - Country Support SCO - Investigation | Savers - USCAN Investigation - Done, Savers - Password Complexity Investigation - Done, Bootcamp training, FDE Conference | Waiting for new task
2021-11-04 | 9:54 | 44504.9613 | Waiting for new task | Savers - Express Replication new build - Setup/Test - Done | Savers - New Platform - Setup/Test
2021-11-05 | 44505.3894 | 44505.9925 | Savers - New Platform - Setup/Test | Savers - POS/GSBO New Platform - Setup/Test - OnGoing, Bootcamp Training | Savers - POS/GSBO New Platform - Setup/Install
2021-11-08 | 44508.4137 | 44508.9327 | Savers - New Platform GSBO / POS - Setup/Test | Savers - New Platform GSBO / POS - Setup/Testing - OnGoing | Savers - New Platform GSBO / POS - Setup/Test
2021-11-09 | 9:57 | 44509.9759 | Savers - New Platform GSBO /POS - Setup/Test | Savers - New Platform GSBO /POS - Setup/Test - OnGoing | Savers - New Platform GSBO /POS - Setup/Test
2021-11-10 | 44510.4108 | 44510.7909 | Savers - New Platform GSBO / POS Possible new build | Savers - New Platform GSBO / POS - Setup/Install - Done | Savers - New Platform GSBO / POS Possible new build
2021-11-11 | 44511.397 | 44511.7887 | Savers - New Platform GSBO / POS Possible new build | Savers - New Platform Desktop Mgr Issue - Waiting for Info | Savers - New Platform Desktop Mgr Issue
2021-11-12 | 44512.3875 | 23:25 | Savers - New Platform Desktop Mgr Issue | Savers - New Platform Desktop Manager Issue - Investigation - Done Savers - New Platform Password Complexity - Investigation - OnGoing | Savers - New Platform Password Complexity
2021-11-13 | 44513.9864 | 44513.9876 | Do 56575 | Finished 33333 | Do 78900000 | Ret 3434